## PLEASE READ
Mentor to Update details
Mentor ID | 2090196
Mentor Name | Vindhyachal Tiwari
Mentee ID | 2217822
Mentee Name | l
|  | # | General instructions for the MENTOR | General instructions for the MENTEE
|  | 1 | Understand mentee's FSE skills (mainly microservices, frontend, cloud) Guide mentee on any additional offline learning that might be needed to complete the Ucs | Ensure suggested additional learnings are completed within suggested timelines
|  | 2 | Identify 2 end-to-end use-cases that are client context-sensitive and they can be completed within 5 business days | Understand use-cases and clarify any questions during the scheduled time
|  | 3 | Schedule daily stand-up with mentee based on your availability and update Daily Tracker worksheet & keep it on Teams folder | Attend the Daily Stand-up without fail. If unable to join due to any unforeseen circumstances, mentee shall inform mentor proactively thru an email Provide accurate status on all action items provided by mentor
|  | 4 | Mentoring plan shared in little broad-based to provide flexibility to the mentors. Mentor can fine-tune the plan based on UC specifics, without compromising on the overall timelines and quality of implementation | Adhere to the implementation timelines determined by the mentor without compromising on quality of implementation
|  | 5 | If there are any major deviations from the plan, please bring this to Chapter Leaders and CMs notice immediately | If stuck with any issues, pls reach out to mentor immediately and also utilize the Teams channel so that Chapter Leaders and CMs can jump in to support

## Milestone Plan
Data Loader Portal
The client would like to develop a Data Loader Portal application to store and process the Patient and his Prescription details through Data Loader Portal to Downstream Systems. Scope of this application would be, 1. Patient Induction – used by admin to register the details of patient into the system. The system stores the details of the Patient and his Prescription Details in the system and able to edit it. The Patient and his prescription details available in the excel sheet. 2. Process Data – The user should be able to send Patient Information to Downstream system. (Just Change the Status to Processed from Inducted)
Program Start Date: Sep 28, 2022 End Date: Oct 11, 2022
# | Activity | Day | Start Date | End Date | Status | Indicative Duration (hrs) | Scoring Out of 5 | Mentee | Mentor | Chapter Lead | Community Manager | Additional Remarks, if any
1 | Complete understanding of requirements document | D0 | 2022-09-28 | 2022-09-28 | Completed | 2 | 5 | Neelima | Vindhyachal
2 | Prepare the DB design for storing asset configurations with DB scripts for the data model. DB to be created at cloud & consumed from there. | D1 | 2022-09-28 | 2022-09-28 | Completed | 2 | 4 | Neelima | Vindhyachal
3 | Prepare the Microservices design (with call flow & field level details) for all the services 1. Login 2. Process & Load Patient Data 3. Search & update patient information 4. Search & update only patient status | D1 | 2022-09-28 | 2022-09-28 | Completed | 5 | 5 | Neelima | Vindhyachal
Iteration #1 - End-to-end implentation of UC1, 2
4 | Prepare UI screens for the below use -cases (along with all validations) 1. Login 2. File Upload (Patient Induction) | D2 | 2022-09-29 | 2022-09-29 | Completed | 9 | 4 | Neelima | Vindhyachal
5 | Implement the Micrservice - for login & File process, upload | D3 | 2022-09-30 | 2022-09-30 | Completed | 9 | 3 | Neelima | Vindhyachal
6 | Integrate the the React/Angular UI with the microservice | D4 | 2022-10-03 | 2022-10-03 | Completed | 5 | 5 | Neelima | Vindhyachal
7 | Complete the Functional testing of login &registration flow - Integration testing of UI & Backend | D4 | 2022-10-03 | 2022-10-03 | Completed | 4 | 5 | Neelima | Vindhyachal
8 | Implement the JUNIT's/Jasmine test cases for all components- Coverage at 70% | D5 | 2022-10-07 | 2022-10-11 | Completed | 4 | 4 | Neelima | Vindhyachal
9 | Iteration #1 Demo | D5 | 2022-10-06 | 2022-10-06 | Completed | 4 | 4 | Neelima | Vindhyachal
10 | Chapter Lead & CM review | D5 | 2022-10-13 | 2022-10-13 | Completed |  | 4 | Neelima | Vindhyachal
Iteration #2 - End-to-end implentation of UC3, 4
11 | Prepare UI screens for the below use -cases (along with all validations) 1. Patient Update 2. Process Patient Data | D6 | 2022-10-06 | 2022-10-06 | Completed | 9 | 4 | Neelima | Vindhyachal
12 | Implement the Micrservice - for Patient search, patient data & status update | D7 | 2022-10-07 | 2022-10-07 | Completed | 9 | 4 | Neelima | Vindhyachal
13 | Integrate the the React/Angular UI with the microservice - for member search & submission | D8 | 2022-10-10 | 2022-10-10 | Completed | 5 | 4 | Neelima | Vindhyachal
14 | Complete the Functional testing of member search & submission flow - Integration testing of UI & Backend | D8 | 2022-10-10 | 2022-10-10 | Completed | 4 | 4 | Neelima | Vindhyachal
16 | Implement the JUNIT's/Jasmine test cases for all components - Coverage at 70%. | D9 | 2022-10-11 | 2022-10-12 | Completed | 4 | 4 | Neelima | Vindhyachal
17 | Iteration #2 Demo | D10 | 2022-10-13 | 2022-10-13 | Completed | 2 | 4 | Neelima | Vindhyachal
18 | Cloud deployment & Review Comments | D10 | 2022-10-13 | 2022-10-14 | Completed | 4 | 4 | Neelima | Vindhyachal
19 | Chapter Lead & CM review |  | 2022-10-17 | 2022-10-17 | Completed |  | 4 | Neelima | Vindhyachal
20 | Fully integrated demo - All services, UI and features | D10 | 2022-10-18 | 2022-10-18 | Completed |  | 4
83.16%

## Daily Tracker
To be filled-in by the mentor during the daily stand-up calls | [8 empty] | Priority | Status
[9 empty] | High | Yet to start
# | Days | Date | Description of bug / implementation approach | Action items for mentee to fix | Priority | ETA for fixing | Status | Mentor Remarks, if any | Medium | In-progress
1 | D0 | 2022-09-28 | [6 empty] | Low | In issue clarification
2 | D1 | 2022-09-29 | [7 empty] | Reviewed
3 | D2 | 2022-09-30 | [7 empty] | Completed
4 | D3 | 2022-10-03
5 | D4 | 2022-10-04
6 | D5 | 2022-10-06
7 | D6 | 2022-10-07
8 | D7 | 2022-10-08
9 | D8 | 2022-10-09
10 | D9 | 2022-10-10
11 | D10 | 2022-10-11